Kailash HMS

AI-First Hospital Management System

Document 06 — Plan

Implementation Plan

UI-first → data → backend → integrations — phased delivery roadmap

| Version | v1.0 |
| --- | --- |
| Date | 01 Jun 2026 |
| Author | Solution Architecture Team |
| Status | Issued for review |

Confidential — internal architecture & planning artefact

# Contents

Right-click → Update Field to populate the table of contents.

# 1. Strategy

v1.0 is delivered in four overlapping arcs. The UI fabric is already built; the priority is to wire it to a real backend without breaking the design language.

Arc A — UI polish & gaps: close the remaining UX gaps (GAP-040 … 049) without changing data shape.

Arc B — Data layer: introduce DB + repositories; switch reads from in-memory to API.

Arc C — Backend & auth: REST + Server Actions + OIDC; complete RBAC server-side.

Arc D — Integrations & AI: real LLM gateway, payment, WhatsApp, lab/HL7, observability.

# 2. Phasing Overview

| Phase | Length | Goal | Exit |
| --- | --- | --- | --- |
| P1 UI close-out | 2 weeks | Close UX / responsive gaps; freeze design tokens. | All UI gaps Closed; Storybook live. |
| P2 DB & repos | 3 weeks | Postgres + repositories + read-only API. | All staff pages render against API; localStorage off. |
| P3 Write paths | 4 weeks | All mutations hit API; audit-log is the source of truth. | Audit chip counts match DB; soft-delete only. |
| P4 Auth & RBAC | 2 weeks | OIDC, refresh-token rotation, server-side canDo. | Login through IdP; role grants from JWT claims. |
| P5 AI gateway | 2 weeks | Real LLM vendor; HITL preserved; per-service config. | All 38 services route through gateway; logs in DB. |
| P6 Integrations | 3 weeks | UPI / WhatsApp prod / Email-SMS / Aadhaar OTP. | Pre-auth via TPA stub; UPI test mode complete. |
| P7 Observability & DR | 1 week | Logs/metrics/traces; backup-restore drill. | SLOs publishing; restore evidence. |
| P8 Hardening & UAT | 2 weeks | OWASP, security review, UAT cycle. | Sign-off from COO / MS / DPO / Finance. |

# 3. Sprint Plan

## Sprint 1 — UI close-out (Phase 1)

| Task | Closes | Acceptance |
| --- | --- | --- |
| Storybook for ui/* and clinical/* | GAP-040 | All shared components have stories |
| WCAG sweep — focus rings, ARIA labels, live regions | GAP-041 | Lighthouse a11y ≥ 95 on key pages |
| Phone (390 px) walk-through of doctor + nurse + ER | GAP-042 | Puppeteer phone sweep green |
| i18n key audit; add missing Hindi strings | GAP-043 | next-intl test passes; no missing-key warnings |
| Replace alert() / confirm() with Dialog component (statutory, refund) | GAP-044 | Zero alert/confirm in src/ |
| Empty / loading / error state coverage on every list | GAP-045 | Visual sweep finds no spinner-only states |
| Activity graph: server-side aggregation prep | GAP-046 | Endpoint shape agreed with backend |

## Sprint 2 — DB foundation (Phase 2)

| Task | Closes | Acceptance |
| --- | --- | --- |
| Postgres v0 migration: tenants, roles, staff, credentials | GAP-010 | Migration green on dev + staging |
| Repository pattern (tsx + zod schemas mirror DB tables) | GAP-011 | Repos covered by unit tests |
| Read-only API for staff (admin), shift, credential | GAP-012 | Admin pages render from API |
| Replace localStorage in useHRStore / useShiftStore / useVendorStore | GAP-013 | StoreHydrator no longer touches these stores |

## Sprint 3 — Patient & visit (Phase 2 cont.)

| Task | Closes | Acceptance |
| --- | --- | --- |
| Migrations v1 — patient, visit, encounter, note | GAP-015 | Patient CRUD in admin |
| Reception walk-in registration writes to DB | GAP-016 | Front-desk e2e green |
| Doctor OPD reads queue + writes note via API | GAP-017 | Doctor e2e green |
| DPDP record-access log fires on chart open | GAP-020 | Audit + DISHA event visible |

## Sprint 4 — Orders, Rx, Pharmacy (Phase 3)

| Task | Closes | Acceptance |
| --- | --- | --- |
| Migrations v2-v3 — order, prescription, drug, pharmacy_claim | GAP-019 | Drug master loaded |
| Drug-safety engine runs server-side; envelope returned to client | GAP-021 | All 4 checks fire; deterministic |
| Pharmacy queue + dispense events end-to-end | GAP-022 | Bedside dispense recorded |
| Narcotic register with sign-out trail | GAP-026 | Two-signatory enforced; audited |

## Sprint 5 — Lab & Radiology (Phase 3)

| Task | Closes | Acceptance |
| --- | --- | --- |
| Migrations + APIs for lab_result + rad_report | GAP-025 | Lab inbox / verify chain green |
| Reflex rules engine on server (no client guesswork) | GAP-028 | Reflex panel auto-added in tests |
| Critical-value notification path to doctor + nurse | GAP-029 | Pager + audit + banner |

## Sprint 6 — IPD, MAR, Discharge (Phase 3)

| Task | Closes | Acceptance |
| --- | --- | --- |
| IPD stay + bed assignment + vitals | GAP-030 | Bed map live; transfers cascade |
| MAR — due / on-time / late / missed states | GAP-032 | Nurse e2e green |
| Discharge 4-pillar gate; freeze bill on confirm | GAP-033 | Discharge e2e green |
| AI discharge summary (HITL) calls gateway | GAP-034 | Doctor signs the summary |

## Sprint 7 — Billing & Insurance (Phase 3)

| Task | Closes | Acceptance |
| --- | --- | --- |
| Bill line auto-population from orders / drugs / bed / procedures | GAP-023 | Bills reconcile to lines |
| Duplicate-charge AI flag with deterministic checks (server) | GAP-024 | Block submit on flagged lines |
| Pre-auth lifecycle + denial-risk AI envelope | GAP-036 | Risk score visible; gated approval |
| Refund two-step approval | GAP-037 | Audit + state machine |

## Sprint 8 — Auth & RBAC (Phase 4)

| Task | Closes | Acceptance |
| --- | --- | --- |
| OIDC integration; password fallback removed at IdP | GAP-001 | All roles login via IdP |
| JWT + refresh rotation; reuse detection | GAP-002 | Test for stolen refresh fails closed |
| Server-side canDo on every mutation | GAP-003 | RBAC bypass attempts denied + audited |
| Aadhaar OTP / DigiLocker patient onboarding (opt-in) | GAP-004 | Patient verified end-to-end |

## Sprint 9 — AI gateway (Phase 5)

| Task | Closes | Acceptance |
| --- | --- | --- |
| src/ai-services/_gateway.ts — vendor abstraction | GAP-014 | All 38 services route through it |
| Per-service config (model, budget, fallback) in admin UI | GAP-038 | Switching vendor takes < 1 minute |
| AI evidence table + DPDP-aware redaction in logs | GAP-039 | PHI not stored verbatim |
| Recall-cohort and quality-intelligence services | GAP-047 | Real outputs in /quality |

## Sprint 10 — Integrations (Phase 6)

| Task | Closes | Acceptance |
| --- | --- | --- |
| WhatsApp Business API production wire-up | GAP-018 | OTP + reminders fire in staging |
| UPI payment gateway test-mode | GAP-024 | Bill paid via UPI captured |
| Email + SMS service abstraction | GAP-048 | OTP and notifications send |
| Lab analyser bridge (HL7 v2) — read-only spec | GAP-005 | Decision deferred to v2; spec written |

## Sprint 11 — Observability + DR (Phase 7)

| Task | Closes | Acceptance |
| --- | --- | --- |
| Pino structured logs + request IDs everywhere | GAP-049 | Log search returns by request_id |
| Prometheus metrics + Grafana board (latency / errors) | GAP-050 | SLOs computed; dashboard URL in TRD |
| Backup nightly + restore drill | GAP-051 | Restore drill green; evidence captured |

## Sprint 12 — Hardening + UAT (Phase 8)

| Task | Closes | Acceptance |
| --- | --- | --- |
| Pen-test + OWASP Top-10 sweep | GAP-052 | Critical / High findings = 0 |
| NABH evidence pack rehearsal (all 9 chapters) | GAP-053 | Pack reviewed by QM |
| UAT cycle by COO / MS / Finance / DPO | GAP-054 | Sign-off recorded |
| Production cutover plan + runbook | GAP-055 | Runbook executed in DR drill |

# 4. Milestones & Dates (illustrative)

| Milestone | Sprint | Target |
| --- | --- | --- |
| UI gaps closed; Storybook live | S1 | Wk 02 |
| DB read-only for staff / shift / vendor | S2 | Wk 05 |
| Patient + Visit live | S3 | Wk 08 |
| Rx + drug-safety + pharmacy live | S4 | Wk 12 |
| Lab + radiology live | S5 | Wk 15 |
| IPD + MAR + Discharge live | S6 | Wk 18 |
| Billing + Insurance live | S7 | Wk 21 |
| OIDC + server-side RBAC | S8 | Wk 23 |
| AI gateway | S9 | Wk 25 |
| Integrations | S10 | Wk 28 |
| Observability + DR | S11 | Wk 29 |
| UAT + cutover | S12 | Wk 31 |

# 5. Resourcing (indicative)

| Role | Headcount |
| --- | --- |
| Tech Lead | 1 |
| Senior frontend engineer | 2 |
| Senior backend engineer | 3 |
| DevOps / SRE | 1 |
| UX designer | 1 |
| QA engineer (incl. e2e) | 2 |
| Domain analyst (clinical) | 1 |
| DPO / Compliance | 0.5 (shared) |
| Project manager | 1 |

# 6. Risk Register (top 10)

| # | Risk | Mitigation |
| --- | --- | --- |
| R1 | LLM vendor decision delayed | Lock gateway abstraction first; pluggable vendors. |
| R2 | IdP integration drags | Allow internal-OIDC stub for staging; cutover late. |
| R3 | Drug master licensing | Engage with ICDR/Pharmacy Council early. |
| R4 | DPDP rules change | Keep consent + RTBF tables generic; quarterly review. |
| R5 | Lab analyser vendor lock-in | Defer to v2; manual entry in v1. |
| R6 | Multi-branch creep | Keep BranchId enum; v2 only. |
| R7 | AI hallucination on safety surfaces | Deterministic gates for safety; LLM never blocks. |
| R8 | Audit table volume | Partition by month; cold-tier > 1 yr. |
| R9 | Phone-mode regressions | Phone sweep in every release. |
| R10 | Pen-test findings late | Run an early hardening sprint (S11.5). |

# 7. Definition of Done (per sprint)

Typecheck clean; lint clean; unit tests added for new logic.

Puppeteer e2e sweep for the affected role passes 0 errors.

Audit chip counts match DB row counts on a fresh smoke test.

All acceptance criteria in the sprint table green.

Documentation updated — BRD / TRD / Schema / Gap rows flipped to Closed.

Per-feature gate: visible screenshot proof attached to PR.

# A. Version History

| Version | Date | Author | Notes |
| --- | --- | --- | --- |
| v1.0 | 01 Jun 2026 | Solution Architecture Team | Initial issue. Dates are sprint-relative, not calendar-locked. |